## Marketing Plan Data
| Marketing Plan Data | [6 empty] | STATUS COLOR LEGEND & TOGGLE
Marketing Plan Lists
[5 empty] | Not Started | In Progress | Delayed | Complete | Quote Needed | Waiting on Quote | Custom 3 | Custom 4
[5 empty] | ON | ON | ON | ON | ON | ON | OFF | OFF
| TASK | CATEGORY | STATUS | % COMP | OWNER | ASSIGNED TO | ANTICIPATED START DATE | ANTICIPATED END DATE | ACTUAL START DATE | ACTUAL END DATE | ESTIMATED COST | ACTUAL COST
1 | Website Development | IT | In Progress | 60% | Darya Loboda | Darya Loboda |  | 2026-09-18 |  |  | 400
2 | Website Changes for Information | IT | In Progress |  | Darya Loboda | Darya Loboda |  | 2026-09-18
3 | GHL Account creation | Marketing | Done |  | Darya Loboda | Darya Loboda |  | 2026-09-18
4 | GHL Phone System setup | Marketing | Not Started |  | Darya Loboda | Darya Loboda |  | 2026-09-24 |  |  | 15
5 | GBP Creation | IT | In Progress |  | Darya Loboda | Darya Loboda |  | 9/22/0216 |  |  | Free
6 | Google Emails | IT | Done |  | Darya Loboda | Darya Loboda |  | 2026-09-16
7 | Sign Design | Marketing | Done |  | Darya Loboda | Darya Loboda |  | 2026-09-16
8 | Compose FB Postings to trucker groups | Marketing | Not Started | 0% | Darya Loboda | Darya Loboda |  | 2026-10-10
9 | Quick Books to WMS Integration | IT | Not Started | 0% | Cesar Ramirez | Maaz |  | 2026-09-30
10 | Trucker flyer for cross-dock volume (post on trucking sites) | Marketing | Not Started |  | Darya Loboda | Darya Loboda |  | 2026-10-10
11 | Paid ads for local businesses needing cross-dock | Marketing | Not Started |  | Darya Loboda | Darya Loboda |  | 2026-10-11
12 | Website to WMS Integration | IT | Not Started | 0% | Maaz | Maaz |  | 2026-09-30
13 | All Platforms Integrated | IT | Not Started | 0% | Maaz | Maaz |  | 2026-09-30
14 | Cameras and Alarm | Vendor Service | Waiting on Quote | 25% | Cesar Ramirez | Cesar Ramirez |  | 2026-10-01 |  |  | 4000
15 | Insurance COI | Vendor Service | Waiting on Quote | 25% | Cesar Ramirez | Cesar Ramirez | 2026-09-30 | 2026-09-30
16 | Company Signs | Vendor Service | Waiting on Quote |  | Darya Loboda | Darya Loboda |  |  |  |  | 15000
17 | Purchase Tablet | Vendor Service | Not Started | 0% | Cesar Ramirez | Cesar Ramirez |  |  |  |  | 1000
18 | Purchase Zebra Printer and Labels | Vendor Service | Not Started | 0% | Cesar Ramirez | Cesar Ramirez |  |  |  |  | 650
19 | Internet or Hot Spot | Vendor Service | Not Started | 0% | Cesar Ramirez | Cesar Ramirez
20 | Purchase Office Furniture | Office | Not Started | 0% | Cesar Ramirez | Cesar Ramirez |  |  |  |  | 400
21 | Floor Markings | Warehouse | Not Started | 0% | Cesar Ramirez | Cesar Ramirez | 2026-10-01 |  |  |  | 346.5
22 | Warehouse Needs (Eyewash,etc) | Warehouse | Not Started | 0% | Cesar Ramirez | Cesar Ramirez | 2026-10-01 |  |  |  | 250
23 | Tier A trucking listings — OLIMP, CrossdockBuddy, DockLinx, XDocks (+ GBP) | Marketing | Not Started |  | Darya Loboda |  |  | 2026-10-10
24 | Publish / lock rate sheet (cross-dock ~$25/pallet; hybrid storage ~$20/pallet/mo; CT parking labeled) |  | In Progress |  | Cesar Ramirez
25 | Bank / ACH payee open for Phoenix Arizona Cross Dock LLC (needed for SBA invoices) |  | Not Started |  | David Molo
22061.5
MARKETING PLAN LISTS

## List Data
Marketing Plan Lists
Marketing Plan Data
NAME | TITLE
Cesar Ramirez | GM | Warehouse
Darya Loboda | Marketing Manager | IT
David Molo | Owner | Vendor Service
Maaz | IT | Office
Marketing
MARKETING PLAN DATA